## Sheet1
Lesson # | Title | Released | Project | Script Words | Act/Est Run Time | Video Plan | Camtasia | Desc TXT | Recorded | Comment
1-1 | Introduction | Done/Live | y | 781 | 8.45 | y | y |  | y
1-2 | PSoC Creator IDE | Done/Live | y | 830 | 6.9333 | y | y |  | y
1-3 | Hello World | Done/Live | y | 1196 | 11.1 | y | y |  | y
1-4 | FreeRTOS | Done/Live | y | 555 | 5.6667 | y | y |  | y
2-1a | UART |  | y | 711 | 6.7714 |  |  |  | WW13
2-1b | Create the main controller |  | MC2-1-uart | 971 | 9.2476 |  |  |  | WW13
2-2a | PWM |  | y | 739 | 7.0381 |  |  |  | WW13 | add a description of how a pwm works… and
2-2b | add the pwm to the main controller |  | MC2-2-PWM | 1631 | 15.5333 |  |  |  | WW13
2-3a | I2C |  | y | 609 | 5.8 |  |  |  | WW13
2-3b | add the i2c to the main controller |  | MC2-3-I2C | 814 | 7.7524 |  |  |  | WW13
2-4a | Kill Switch |  | 2-4 Kill Switch | 722 | 6.8762 |  |  |  | WW13
2-4b | add kill switch to the main controller |  | MC2-4-KillSwitch | 761 | 7.2476 |  |  |  | WW13
2-5a | CapSense |  | 2-5 capsense motor | 910 | 8.6667 |  |  |  | WW13
2-5b | Add the capsense to the main controller |  | MC2-5-Capsense | 469 | 4.4667 |  |  |  | WW13
2-6 | Basic Thermistor |  | 3-5-basictherm | 1800 | 17.1429 |  |  |  | WW13
2-7 | Tracealyzer |  | n |  | 0 |  |  |  | WW13
3-1 | Intro to BLE & Find Me |  | 3-1-blefindme | 1973 | 18.7905 |  |  |  | WW13 | fix the syscall priority
3-2a | Simple BLE Custom Service |  | 3-2-simplebleperipheral | 1515 | 14.4286 |  |  |  | WW13
3-2b | Add ble to the main controller |  | MC3-2-BLE | 1383 | 13.1714 |  |  |  | WW13
3-3a | Simple BLE Central control of LED Service 3-2a |  | 3-3-simpleblecentral | 2227 | 21.2095 |  |  |  | WW13 | fix the syscall priority
3-3b | Make the first Remote Control Project (uart) |  | rc3-3b-uart | 810 | 7.7143
3-4 | Add CapSense to remote control |  | rc3-4 CapSense | 723 | 6.8857
3-5a | Basic Motion Sensor |  | 3-5-basicmotion | 1384 | 13.181 |  |  |  | WW13
3-5b | Add motion sensor to remote control |  | rc3-5b-Motion | [5 empty] | WW13
4-1 | AFE Shield POT | Q418 | [7 empty] | April
4-2 | AFE Shield OLED | Q418 | [7 empty] | April
4-3 | AFE Shield Ambient Light | Q418 | [7 empty] | April
4-4 | AFE Shield Sensor Hub | Q418 | [7 empty] | April
3-8 | E-Ink Display Basic | Q218
3-9 | E-Ink Display Integrated | Q218
3-10 | Low Power Design Best Practices | Q318 | [7 empty] | April
3-11 | SMIF Basic | Q318 | [7 empty] | April
3-12 | SMIF Integrated | Q318 | [7 empty] | April
5-1 | WiFi 1 TBD | Q318
5-2 | WiFi 2 TBD | Q318
5-3 | WiFi 3 TBD | Q318
5-4 | WiFi 4 TBD | Q318
6-1 | Security 1 TBD | Q418
6-2 | Security 2 TBD | Q418
6-3 | Security 3 TBD | Q418
6-4 | Security 4 TBD | Q418
7-1 | Complete Project Summary | Q418